## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | Sept 6th 2024 - Sept 25th 2024 | - identified and researched feasibility and time requirement for the project idea - discussed and finalized user flow(how a user will interact with the application) - created tentative UI design for prototyping - researched and finalized database engine(postgres) - finalized techstack - initial code setup for backend and frontend done - SSO with OAuth2.0 implemented in backend - Set up Git with required branching strategy and merge restrictions | - needed database solution for faster reads - cross-platform development environment setup for everyone caused a few bugs | - Imprecise Sprint Goals and Objectives | Set specific, measurable, achievable, relevant, time-bound goals for the project and regularly review progress against these goals. | 8 | 4 | 4 | 0 | 8 | 98.5 | 66.5 | 32 | 12.5 | 9 | 7.5 | 18 | 0 | 12 | 13 | 9
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Tushar Kendre
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 3 | 1 | 2 | 1 - define high level requirements 2 - research techstacks in accordance to requirements 7 - research similar products |  | 1 | 1 |  |  |  |  | 2 | Defined and researched all possible solutions based on project requirement as well as current similar technologies | - | - | 1 - Finalize tech stack 2 - Start SSO setup | 5
2 | 09/15-09/21 | 4 | 3 | 1 | 1 - Finalize tech stack - database and api engines 2 - Research different SSO solutions | 2 |  | 2 | [5 empty] | Finalized and started work on creating a dev directory structure for apis, finalized database as postgresQL, started work on SSO setup | Difficulty in understanding OAuth2.0 client side and server side authentication and verification | Read up on the documentation | 3 - Complete dev directory structure setup 5 - Get dev code running on everyone's machines 3 - SSO setup for APIs | 5
3 | 09/22-09/28 | 5 | 3 | 2 | 3 - Set up whole development environment 5 - Install required packages/softwares for running dev environment on everyone's machines 3 - SSO setup for APIs with OAuth2.0 |  |  |  | 4 |  | 1 |  |  | Implemented fastify based api framework with authentication using keycloak(OAuth2.0), communicated code running instructions and got it running on everyone's computers, discussed dev workflow and code structure to be followed | Difficulty in setting up on multiple different environments(Windows, Mac, etc.) in docker | Researched online for known issues and got it fixed | 2 - Start setting up database 3 - Create CRUD APIs 5 - Communicate code contribution instructions | 5

## Faizan Ahmad
Your Lead Roles: Design and Implementation Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 4 | 2 | 2 | 1 - define high level requirements (functional/non-functional) 2 - researched tech stacks and different database 6 - setup git and ssh in new machine |  | 1 | 1 |  |  |  | 1 |  | Discussed and defined high level requirements for the project. Research different databases (both SQL/NoSQL) that can cater to our usecases. Researched different types of system architectures that we can use for our project | - | - | 1 - Finalize tech stack & DB 2 - Initial DB design | 5
2 | 09/15-09/21 | 4 | 3 | 1 | 1 - Finalize tech stack & DB 2 - Initial DB design |  | 1 | 2 | [5 empty] | Completed research on a reasonable tech stack for our project. Completed research on most appropriate system designs for our project. Used dbdiagram.io to create an initial DB design for our tables based on the initial high level requirements. | - | - | 3 - Create and configure React for our web app 6 - Setup dev code with help from Tushar 6 - Configure monorepo's project-level settings for eslint, prettier and add precommit Git Hooks | 5
3 | 09/22-09/28 | 8 | 6 | 2 | 6 - Set up whole development environment including Docker, Redis, Postgres, Postman, Prisma etc 3 - Created boilerplate React App for everyone to use 3 - Configured project-level Prettier and Eslint for code formatting 3 - Added precommit git hook for formatting |  |  |  | 4 |  |  | 2 |  | Created and setup the React App for our web app. Configured Eslint and Prettier for code formatting and linting to maintain coding standards. Added a precommit git hook to format all staged files based on prettier and eslint rules setup in the config to streamline coding standards. | Difficulty in setting up git hooks through husky since project root and workspace root were different | Fixed the issue by manually overriding git configs, specifically core.hooksPath to read code/.husky as the hooks root | 3 - Add database tables 3 - Create CRUD APIs with team 2 - System design for analytics 1 - Research on configuring K8, EC2, AWS EKS, and AWS Elastic Beanstalk | 10

## Jaindra Parvatheneni
Your Lead Roles: Config Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8 - 09/14 | 11 | 9 | 2 | 0 - learn git and read some tutorials, Learn about Figma 1 - define high level requirements 6 - set up git in my system 5 - Help team members in setting up git, Send reminders to team members to set up git in their systems | 2 | 1 |  |  |  | 5 | 1 |  | 1. Set up git 2. Commit changes to Lab1 and Merge to main | 1. Ran into a problem which erased the commited changes while merging lab1 into main 2. Local git had some authorization issues. | 1. Was able to merge the branches successfully 2. Used codes which bypassed the issues | 0 - Read React tutorials 1 - continue to define requirements 3 - Update Figma document | 6
| 09/15 - 09/21 | 5 | 3 | 2 | 0 - Read React tutorials 2 - set up inital git action 5 - Remind team members to pull new changes 7 - submit lab1 assignment | 1 |  | 0.5 |  |  | 0.5 |  | 1 | 1 - set up git restriction rule before merges 2 - Helped refine the project design 3 - Started working on figma | - | - | 1 - setting up working environment 2 - set up git branching stategy | 5
| 09/22 - 09/28 | 6.5 | 4.5 | 2 | 6 - Set up the environment, git branching strategy 7 - finish the sppp document, presentation ppt | [6 empty] | 1.5 | 3 | 1 - finished the project presentation ppt 2 - finished setting up the environment | 2 - Had port issues | 2 - using a different host from everyone else in the team, should cross verify everything before comming merges in the future | 1 - finish figma dessign | 2

## Amruth Reddy
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 4 | 3 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - Disucced in team meeting about the idea, execution 6 - set up git 7 - research similar products, prepare presentation | 0.5 | 0.5 |  |  |  | 1 | 1 |  | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | Encountered a hashing problem | Resolved it by adjusting configuration settings. | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/8-09/14 | 6.5 | 4.5 | 2 | 0 - Continue learning Git and Django, especially focusing on version control and branching. 1 - Refine high-level requirements based on team discussions and finalize the project's direction. 5 - Collaborate in team meetings to discuss UI design, MVP features, security considerations, and assign backend/frontend tasks. 6 - Assist with setting up GitHub protocol, commit guidelines, and ensure all systems are configured correctly. 7 - Explore tech stack (Fastify, Prisma, Redis) and review similar tools to understand potential implementation strategies. | 0.5 | 0.5 |  |  |  | 2 | 1 | 0.5 | 0 - Learning Git and Django: Practiced Git branching, completed advanced Django tutorials. 1 - Requirement Analysis: Contributed to project direction and app focus. 5 - Team Collaboration: Participated in meeting, documented minutes, finalized MVP. 6 - Git Setup: Established GitHub protocol, debugged setup, configured tools. 7 - Tech Stack Research: Researched Fastify, Prisma, Redis, shared insights. | - | - |  | 4
2 | 09/15-09/21 | 4 | 3 | 1 | 0 - Learning Git and Django: Integrate Django with APIs, enhance Git collaboration. 1 - Requirement Analysis: Validate and refine MVP requirements. 5 - Team Collaboration: Review implementation, adjust plans. 7 - Tech Stack Implementation: Implement CRUD with Fastify, Prisma, and test with Redis. | 0.5 | 1 |  |  |  | 1 |  | 0.5 | 1- Write 1 sections of SPPP: Drafted and reviewed a key section of the SPPP 5- Participate in Iteration 0 presentation: Actively participated in the presentation, contributed to discussing the UI design, tech stack, and MVP features. | - | - | 0 - Learning Git and Django: Continue improving Django skills with a focus on forms and advanced Git commands. 1 - Requirement Analysis: Refine the project’s requirements and finalize MVP feature details. 5 - Team Collaboration: Prepare for the next meeting by reviewing progress and addressing any blockers. 6 - Git Setup: Ensure all team members are following Git commit protocols and resolve any Git-related issues. 7 - Tech Stack Implementation: Start building backend routes with Fastify, integrate Prisma, and test Redis caching functionality. | 5

## Shubh Gupta
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 5 | 3 | 2 | 0 - Researched about testing methods and automation. 1 - Explored Prettier and Eslint 6 - Setup git and updated a file | 1 |  | 1 |  |  |  | 1 |  | Discussed testing methods and ways to automate it in the application. Explored Prettier and ESlint for the same. Setup Git, Cloned the team repo on local machine and updated the Team.md file. | - | - | 0 - Research about different types of testing methods and deffects and ways to handle them. 1 - Ways to automate testing 4 - Finalizing testing metrics | 5
2 | 09/15-09/21 | 5 | 4 | 1 | 0 - Research about different types of testing methods and deffects and ways to handle them. 1 - Ways to automate testing 4 - Finalized testing metrics | 2 | 2 | [6 empty] | Learnt about Unit testing, Integration tesing and react specific tesing. Finalized Prettier and Eslint for automating code formatting. Finalised the testing metrics for the project going forward and the code review process before pushing anything to the main branch. | - | - | 6 - With Tushar and Faizan's help, setup the development environment including Docker, Redis, Postgres, Postman, Prisma, etc. 3 - Configured project-level Prettier and Eslint for monorepo and added precommit git hook for formatting | 5
3 | 09/22-09/28 | 8 | 6 | 2 | 6 - With Tushar and Faizan's help, setup the development environment including Docker, Redis, Postgres, Postman, Prisma, etc. 3 - Configured project-level Prettier and Eslint for monorepo and added precommit git hook for formatting |  |  |  | 4 |  |  | 2 |  | Setup the development enviroment including react, docker, and postman. Finalized Prettier and eslint for automated code formatting including plugins for node recommended formatting, react recommended formatting and typescript recommended formatting |  |  | 4 - Code review 4 - setup Gitflow | 5

## Hemant Krishnakumar
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 4 | 2 | 2 | 0 - learn git and figma, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | 1 |  |  |  | 0.5 | 1 | 0.5 | Learnt and set up git, defined high level requirements, made a draft plan and did basic research on the project | - | - | 0 - learn react 1 - continue to define requirements 3 - implement a designs on Figma | 5
2 | 09/15-09/21 | 5.5 | 3.5 | 2 | 0 - learn react 3 - implement designs for figma 5 - send reminders to the team and provided support 6 - setup full stack and env | 1 |  |  | 3 |  | 0.5 | 1 |  | Completed initial designs, environment setup, and team coordination | Difficulty in setting up the full stack | Resolved with team and additional support | 0 - learn react 1 - continue to define requirements 3 - continue Figma design 6 - finish setting up env | 5
3 | 09/22-09/28 | 6.5 | 3 | 2 | 0 - learn react 3 - implement designs for figma 5 - send reminders to the team and provided support 6 - setup full stack and env 7 - prepare documents | 1 |  |  | 3 |  | 0.5 | 0.5 | 1.5 | Implemented React components, completed Figma designs partially, continued full stack environment setup, and prepared documentation | Encountered difficulties with integrating frontend designs with backend setup | In progress, working with team members to resolve integration challenges and refine setup | 1 - plan sprints 3 - finish figma disgn for MVP 3 - start creating react component codes | 5