## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Requirements | unclear requirements
scope creep
constant requirements changes
Management | improper task assignments | Team members were assigned tasks that didn't align with their skill sets or expertise, resulting in inefficiencies and delays in task completion. This led to a lack of progress on key deliverables and reduced overall productivity. | 2 | 3 | 3 | 36 | Hemant | - | - Redefine Roles: Clearly define roles and responsibilities to ensure alignment. - Task Reallocation: Reassign tasks based on the skills matrix to boost efficiency. - Regular Feedback: Hold bi-weekly sessions to address challenges in task assignments. - Backup Plans: Identify secondary skills to ensure flexibility and avoid bottlenecks | Tasks were misaligned with team skills, causing delays. A skills assessment, task reallocation, and regular feedback will optimize assignments and improve efficiency. | On going
| improper planning | The project planning phase lacked clear timelines, goals, and task prioritization. This resulted in overlapping efforts, miscommunication among team members, and difficulty in tracking progress, ultimately affecting the project's workflow and efficiency. | 2 | 3 | 3 | 36 | Hemant | - | -Define Goals: Reassess goals to ensure they are clear, measurable, and aligned. -Project Timeline: Break down the project into phases with realistic deadlines. -Prioritization: Identify and categorize tasks by urgency and importance. -Resource Allocation: Distribute resources based on availability and project needs. -Regular Checkpoints: Hold weekly meetings to review progress and adjust plans. -Risk Management: Identify risks early and update mitigation strategies regularly. | Unclear goals and poor planning caused setbacks. A structured timeline, task prioritization, and regular progress checks will ensure a more organized and efficient project flow. | On going
Technology competence | Not familiar with the framework used | Certain team members are unfamiliar with the tech frameworks but enough time has been allotted towards each for collaborative learning | 3 | 1 | 2 | 20 | Tushar |  | - Aggregate learning resources after analyzing everyone's needs - One on one sessions arranged for collaborative learning | Currently monitoring everyone's progress with assigned learning resources | Ongoing
Design and implementation | Improper design
improper technology stack
| Messy code | This can cause delays especially during bug fixes. Proper formatting and certain good practices need to be enforced(through code) as well as communicated to everyone | 4 | 4 | 3 | 10 | Tushar, Faizan |  | - Add formatters for every project package - Automated formatting before every git commit | Git rules and formatting has been set up | Done
Testing | Not enough testing
Integration and deployment | Not enough time for integration and deployment