## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | Sept 6th 2024 - Sept 25th 2024 | - identified and researched feasibility and time requirement for the project idea - discussed and finalized user flow(how a user will interact with the application) - created tentative UI design for prototyping - researched and finalized database engine(postgres) - finalized techstack - initial code setup for backend and frontend done - SSO with OAuth2.0 implemented in backend - Set up Git with required branching strategy and merge restrictions | - needed database solution for faster reads - cross-platform development environment setup for everyone caused a few bugs | - Imprecise Sprint Goals and Objectives | Set specific, measurable, achievable, relevant, time-bound goals for the project and regularly review progress against these goals. | 8 | 4 | 4 | 0 | 8 | 72.5 | 66.5 | 6 | 12.5 | 9 | 7.5 | 18 | 0 | 12 | 13 | 9
1 | Sept 26th 2024 - Oct 16th 2024 | Key Achievements: - Setup of GitHub repository, Docker, and initial backend structure. - Implemented signup, login, and resume upload features. - User stories prioritized and tracked using Pivotal Tracker. Good Practices: - Adopted a GitHub branching strategy with individual feature branches. - Pull requests were reviewed by at least two members before merging. - Unit testing for the frontend using Jest, with backend integration tests, and tracked code coverage metrics. - CI/CD setup with GitHub Actions and AWS ECS. | - Faced integration issues and difficulties with unfamiliar technologies. - No major bugs were identified, but the team is working on refining integration and testing processes. | - Challenges in managing user feedback and testing schedules for MVP features. - Coordination of tasks across team members involved in the code review process. | Complete the backend setup for CRUD operations. Perform integration testing between frontend and backend. Implement UI/UX refinements based on feedback. Focus on gathering user feedback and testing MVP features. | 13 | 20 | 35 | 13 | 22 | 102 | 98 | 4 | 10 | 13 | 18 | 24 | 6 | 8 | 7.5 | 11.5
2 | Oct 17th 2024 - Nov 7th 2024 | Key Achievements: - set up a workable front end structure - Apis have been implemented -Backend work has been mostly completed | - no issues found | - faced challenges in collaborating between frontend and backend working team | - planned multiple sprints before the next iteration and gave evryone specific tasks of their own | 5 | 11 | 3 | 3 | 3 | 82.5 | 80.5 | 2 | 13.5 | 1 | 2 | 29 | 2 | 10 | 2.5 | 9
3 | Nov 8th 2024 - December 8th 2024 | Key Achievements: - set up a workable application while succesfully integrating the front end and back end - succesfully tested all features and apis - | - no issues found | - | - Packaged the whole application and presnted it succesfully within the given time period | 10 | - | 11 | 11 | 0 | 127.5 | 123.5 | 4 | 16 | 1 | 0 | 73 | 3 | 13 | 3 | 14.5

## Tushar Kendre
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 3 | 1 | 2 | 1 - define high level requirements 2 - research techstacks in accordance to requirements 7 - research similar products |  | 1 | 1 |  |  |  |  | 2 | Defined and researched all possible solutions based on project requirement as well as current similar technologies | - | - | 1 - Finalize tech stack 2 - Start SSO setup | 5
2 | 09/15-09/21 | 4 | 3 | 1 | 1 - Finalize tech stack - database and api engines 2 - Research different SSO solutions | 2 |  | 2 | [5 empty] | Finalized and started work on creating a dev directory structure for apis, finalized database as postgresQL, started work on SSO setup | Difficulty in understanding OAuth2.0 client side and server side authentication and verification | Read up on the documentation | 3 - Complete dev directory structure setup 5 - Get dev code running on everyone's machines 3 - SSO setup for APIs | 5
3 | 09/22-09/28 | 5 | 3 | 2 | 3 - Set up whole development environment 5 - Install required packages/softwares for running dev environment on everyone's machines 3 - SSO setup for APIs with OAuth2.0 |  |  |  | 4 |  | 1 |  |  | Implemented fastify based api framework with authentication using keycloak(OAuth2.0), communicated code running instructions and got it running on everyone's computers, discussed dev workflow and code structure to be followed | Difficulty in setting up on multiple different environments(Windows, Mac, etc.) in docker | Researched online for known issues and got it fixed | 2 - Start setting up database 3 - Create CRUD APIs 5 - Communicate code contribution instructions | 5
4 | 09/28-10/2 | 6 | 4 | 2 | 1 - Analysed initial database design requirements 2 - Designed database tables for core functionality(sign in, users table, file uploads) 3 - Implemented JWT Token Verification in backend | 0 | 1 | 2 | 1 |  |  |  |  | Implemented basic tables for storing user information, JWT token verification in backend, Postman setup | Keycloak token verification caused issues due to different issuer names in token and request origin from backend | Added web origins policy to allow backend origin | 3 - Implement login, logout, get token and other sso operations in frontend 1 - start database design for other functional APIs | 5
5 | 10/3-10/09 | 6 | 4 | 2 | 3 - Completed frontend setup for SSO operations(login, logout, appropriate redirects, get JWT Token, etc.) 1 - Designed database for core functionalities(create job post, create resume object, etc.) alongwith appropriate relationships |  | 3 |  | 3 |  |  |  |  | Completed login using SSO(keycloak OAuth 2.0) for frontend and appropriate token calls for api requests | - | - | 3 - Implement database design in Prisma 3 - Create CRUD APIs with appropriate operations for atleast one entity | 5
6 | 10/10-10/17 | 5 | 5 | 0 | 3 - Implemented data tables in Postgres via prisma 3 - Created CRUD APIs for Job Listings entity |  |  |  | 5 |  |  |  |  | Implemented all data tables necessary for base functionalities, Created CRUD APIs for job listings with appropriate validations and typed data formats | - | - | 3 - Implement CRUD APIs for other entities 5 - Communicate practices to use while writing API Calls 4 - Setup testing framework for backend
7 | 10/18 - 10/25 | 5 | 4 | 1 | 3 - Created new APIs needed for applicant job listings 3 - Added full text search to job listings |  |  |  | 4 |  | 1 |  |  | Implemented APIs that allow access and search functionality for published public job listings | - | - | 3 - Add slices for created APIs in redux | 5
8 | 10/25 - 11/7 | 5 | 4 | 1 | 3 - Added slices for created APIs in redux |  |  |  | 4 |  | 1 |  |  | Implemented typed reducers with asynchronous calls to the API from frontend | - | - | 4 - Setup and write test cases for completed APIs 3 - Integrate API data fetching from frontend | 5
9 | 11/8-11/15 | 6 | 5 | 1 | 0 - Researched node-tap for automated backend testing 1 - Analyzed and tried different libraries for mocking database calls | 3 | 2 | [6 empty] | Learned and defined required testing framework for backend testing |  |  | 3 - Setting up node-tap 4 - writing basic test cases to start
10 | 11/16-11/23 | 5 | 4 | 1 | 0 - Read up on sinon library for mocking authentication calls 3 - Set up node-tap with sinon for automated testing | 1 |  |  | 3 |  |  |  |  | Node-tap set up to check code coverage | Initial issues with library versions for sinon | Updated typescript compiler config | 4 - Write test cases for further testing
11 | 11/24-1130 | 6 | 5 | 1 | 4 - Brought up backend coverage to 40% 5 - Discussed ongoing tasks and api integration bugs |  |  |  | 5 |  | 1 |  |  | Wrote test cases and created frameworks for testing routes and plugins in the future | - | - | 3 - Finalize API integrations and project completion
12 | 12/1-12/8 | 6 | 5 | 1 | 5 - Final analysis of frontend and backend integration 3 - Implemented api integrations for shortlist, create job listing, resume analysis, job applications |  |  |  | 4 |  | 1

## Faizan Ahmad
Your Lead Roles: Design and Implementation Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 4 | 2 | 2 | 1 - define high level requirements (functional/non-functional) 2 - researched tech stacks and different database 6 - setup git and ssh in new machine |  | 1 | 1 |  |  |  | 1 |  | Discussed and defined high level requirements for the project. Research different databases (both SQL/NoSQL) that can cater to our usecases. Researched different types of system architectures that we can use for our project | - | - | 1 - Finalize tech stack & DB 2 - Initial DB design | 5
2 | 09/15-09/21 | 4 | 3 | 1 | 1 - Finalize tech stack & DB 2 - Initial DB design |  | 1 | 2 | [5 empty] | Completed research on a reasonable tech stack for our project. Completed research on most appropriate system designs for our project. Used dbdiagram.io to create an initial DB design for our tables based on the initial high level requirements. | - | - | 3 - Create and configure React for our web app 6 - Setup dev code with help from Tushar 6 - Configure monorepo's project-level settings for eslint, prettier and add precommit Git Hooks | 5
3 | 09/22-09/28 | 8 | 6 | 2 | 6 - Set up whole development environment including Docker, Redis, Postgres, Postman, Prisma etc 3 - Created boilerplate React App for everyone to use 3 - Configured project-level Prettier and Eslint for code formatting 3 - Added precommit git hook for formatting |  |  |  | 4 |  |  | 2 |  | Created and setup the React App for our web app. Configured Eslint and Prettier for code formatting and linting to maintain coding standards. Added a precommit git hook to format all staged files based on prettier and eslint rules setup in the config to streamline coding standards. | Difficulty in setting up git hooks through husky since project root and workspace root were different | Fixed the issue by manually overriding git configs, specifically core.hooksPath to read code/.husky as the hooks root | 3 - Add database tables 3 - Create CRUD APIs with team 2 - System design for analytics 1 - Research on configuring K8, EC2, AWS EKS, and AWS Elastic Beanstalk | 15
4 | 09/28-10/2 | 13 | 11 | 2 | 0 - Learn how to configure JEST & React Testing Library 0 - Learn how to configure Redux 1 - Finalize db requirements with team 2 - Update database design 2 - Review Figma designs with team 5 - Discussed database design with team | 3 | 1 | 5 |  |  | 1 |  | 1 | Learned how to setup JEST and react testing library in a React App with Vite. Learned how to setup state management using React Redux. Changed DB Design based on updated requirements on dbdiagrams.io and discussed the design and requirements with the team | - | - | 2 - Finalize DB Design and create UML diagrams 3 - Incorporate JEST and add some test cases for reference 3 - Incorporate Redux and create 1 reducer for team to reference 6 - setup JEST with React Testing Library 6 - setup React Redux | 10
5 | 10/3-10/09 | 9 | 8 | 1 | 2 - Finalized DB Design 2 - Created UML Diagrams for DB 3 - Incorporated JEST and added some test cases for reference 3 - Incorporated Redux and created reducer for team to reference 5 - Explained team how tests and redux worked 6 - Setup JEST on my and team's machines 6 - Setup React Redux on my and team's machines |  |  | 3 | 4 |  |  | 1 |  | Completed database design alongwith UML diagrams. Configured JEST and react testing library and created some base test case. Also configured React Redux and started working on creating reducers. Helped the team configure jest redux on their machines. | Difficulty in setting up JEST as it was a bit tricky to configure it with VITE | Read some documentation and updated configs for VITE to work with JEST and react testing library. | 2 - Create the SDD document 3 - Continue Redux and create reducers 4 - Test code during PR review 5 - Configure JIRA workflows and manage sprint being the scrum master 7 - Review PRs from other team members | 10
6 | 10/10-10/17 | 8 | 8 | 0 | 2 - Create the SDD document 3 - Continue Redux and create reducers 4 - Test code during PR review 5 - Configure JIRA workflows and manage sprint being the scrum master 7 - Review PRs from other team members |  | 3 | 2 | 1 |  | 1 |  | 1 | Completed redux implementation with a main reducer for team's reference. Created the SDD document with diagrams. Reviewed PRs by other team members and tested their code. | - | - | 3 - Create Dashboard Layout with Sidebar and Sidebar Items 3 - Create Empty Pages for all Dashboard pages and link them to sidebar items 3 - Create individual reducers for all Dashboard pages 5 - Create new sprint and assign tasks | 15
7 | 10/18 - 10/25 | 13 | 11 | 2 | 0 - Learned how to integrate MUI, themes and Styled Components 3 - Created Basic Layout of Dashboard including Theme 3 - Added a few components for Dashboard including routing 6 - Configured Material UI and theme to work with our web app | 1 |  |  | 9 |  |  | 1 |  | Configure Material UI with theme. Created Dashboard Layout. Handled routing. Created some reusable components | - | - | 3 - Create more components for Dashboard 3 - Create empty pages for different features 3 - Add Charts and cards to view | 10
8 | 10/25 - 11/7 | 11 | 10 | 1 | 3 - Created all major components for Dashboard 3 - Created empty pages for all different features in our dashboard 3 - Added Charts and Cards to view data 3 - Completed UI of Analytics page with dummy data |  |  |  | 10 |  |  |  |  | Created all major components including charts and completed UI of Analytics page with dummy data. Integrated all components with AppTheme and test cases for components | - | - | 3 - Complete Resume Upload and Analysis feature end-to-end 6 - Configure husky to run tests before commits 6 - Configure CI/CD to build backend and frontend | 15
9 | 11/8-11/15 | 7 | 6 | 1 | 2 - Updated the SDD document 3 - Created Resume Uploading 3 - Refactored components for cleanup on FE 3 - Added test cases 5 - Created new sprint and assigned tasks |  | 1 |  | 4 | 1 |  |  |  | Updated SDD. Created Resume Uploading. Refactored components for cleanup. Added FE test cases |  |  | 0 - Research different AI models to integrate 1 - Understand the requirements for the AI analysis 3 - Complete Resume Upload feature 3 - Complete Test cases for components | 5
10 | 11/16-11/23 | 7 | 6 | 1 | 0 - Research different AI models to integrate 1 - Understand the requirements for the AI analysis 3 - Complete Resume Upload feature 3 - Complete Test cases for components | 2 | 1 |  | 3 |  |  |  |  | Learned about functionalities AI models can provide and how to use each one (ChatGPT vs Claude). Also researched some wrapper models. Finally decided to go with Claude which allows uploading a PDF. Also decided on what kind of metrics are needed to show to the user. | - | - | 3 - Add AI integration to Resume Analysis 3 - Add AI integration to Resume against Job Analysis | 10
11 | 11/24-1130 | 12 | 12 | 0 | 3 - Add AI integration to Resume Analysis 3 - Add AI integration to Resume against Job Analysis | 2 |  |  | 10 |  |  |  |  | Implemented an initial API call to Claude. Integrated PDF upload to Claude and tested different Prompts | Faced issue with converting a pdf file into base64String that Claude accepts. Initial challenge was to integrate API call and get response in a certain way | Used Buffer class from node to convert pdf file to base64String. Next I experimented with different prompts to receive a JSON from Claude as a response | 3 - Add AI integration to Resume against Job Analysis 3 - Show AI Analysis on Resume Analysis UI 3 - Show AI Analysis on Resume against Job Analysis 2 - Updated SDD document 6 - Help with AWS Deployment 5 - Update JIRA 2 - Help team create final presentation | 12
12 | 12/1-12/8 | 12 | 11 | 1 | 3 - Add AI integration to Resume against Job Analysis 3 - Show AI Analysis on Resume Analysis UI 3 - Show AI Analysis on Resume against Job Analysis 2 - Updated SDD document 6 - Help with AWS Deployment 5 - Update JIRA 2 - Help team create final presentation |  | 1 |  | 8 |  | 1 | 1 |  | Implemented AI analysis for a Resume against a Job once user applies to a job. Tested with different prompts. Created a new field in DB for Resume Analysis text for all Resume Analysis types. Added analysis scores and review text to Resume Analysis UI. Added AI Match Score for Resume against Job on frontend. Updated SDD and presentation | - | -

## Jaindra Parvatheneni
Your Lead Roles: Config Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8 - 09/14 | 9 | 7 | 2 | 0 - learn git and read some tutorials, Learn about Figma 1 - define high level requirements 6 - set up git in my system 5 - Help team members in setting up git, Send reminders to team members to set up git in their systems | 2 | 1 |  |  |  | 3 | 1 |  | 1. Set up git 2. Commit changes to Lab1 and Merge to main 3. wrote meeting minutes | 1. Ran into a problem which erased the commited changes while merging lab1 into main 2. Local git had some authorization issues. | 1. Was able to merge the branches successfully 2. Used codes which bypassed the issues | 0 - Read React tutorials 1 - continue to define requirements 3 - Update Figma document | 6
| 09/15 - 09/21 | 5 | 3 | 2 | 0 - Read React tutorials 2 - set up inital git action 5 - Remind team members to pull new changes 7 - submit lab1 assignment | 1 |  | 0.5 |  |  | 0.5 |  | 1 | 1 - set up git restriction rule before merges 2 - Helped refine the project design 3 - Started working on figma | - | - | 1 - setting up working environment 2 - set up git branching stategy | 5
| 09/22 - 09/28 | 6.5 | 4.5 | 2 | 6 - Set up the environment, git branching strategy 7 - finish the sppp document, presentation ppt | [6 empty] | 1.5 | 3 | 1 - finished the project presentation ppt 2 - finished setting up the environment for git docker and postman 3. Reviewed PR requests | 2 - Had port issues | 2 - using a different host from everyone else in the team, should cross verify everything before comming merges in the future | 1 - finish figma dessign | 2
| 09/28-10/2 | 3 | 1 | 2 | 6 - setup front-end environemnt | [6 empty] | 1 |  | 1 - helped setup figma components 2 - helped with branching strategy |  |  | 1 - finish figma 2 - learn react | 5
| 10/3 - 10/09 | 5 | 3 | 2 | 0 - learned basic react 2 - worked on Figma | 1 |  | 2 | [5 empty] | 1. Finished the upload JD page 2. finished account settings page 3. Helped identify user stories for pivotal tracker 4. Reviewed PR requests | 2 - deleted the page because of idea differences 3 - pivotal tracker couldnt accomodate the changes | 2 - working on the page with Amruth reddy 3 - switched to jira | 1- finish figma 2 - setup react components | 3
| 10/6 - 10/12 | 4 | 4 | 0 | 2 - wrote react code components for LandingPage and Loginpage, App.tsx 2 - wrote submissions functions 4 - wrote test cases for landing, login, signup and forgot password pages |  |  | 2 |  | 2 |  |  |  | 1. Wrote react code for components on the landing page, loginpage and app files 2. created a new branch to push these changes 3. created new test cases for react components 4. Added submission functions for login, signup and forgotpassword 5. Reviewed PR requests | 2. because i have a different port than the others i cannot merge these changes into the main branch so instead i have updates them on jaireact branch as of now, which stops me from making commits into the main branch 3. Environent was not setup properly which led to errors | 2. working on a solution by collabprating with the team 3. Re-installing packages | 1 - try finding a solution to port issue 2. finish iteration 1 document and presentation ppt 3 - rectify errors | 6
| 10/10 - 10/17 | 4.5 | 4.5 |  | 0 - learn to integrate react in the project 3 - Created test cases for the pages 5 - reviewed pull requests 7 - gave presenation for iteration 1 and worked on | 1 |  |  | 2 |  | 0.5 |  | 1 | 3. created new test cases for react components 5. Reviewed PR requests 7. Gave presenation and worked on ppt | - | - | 1 - finish working on all pages | 2
| 10/18 - 10/25 | 4.5 | 3.5 | 1 | 0 - learn typescript 3 - Made changes to pages with hemant 5 - reviewed pull requests | 2 |  |  | 1 |  | 0.5 |  |  | 1. integrated landing loging and forgotpassword pages with hemant 2. created a new branch to push changes | 2. ran into conflict errors while merging | 1. resolved | 1 - finish working on all pages 3 - rectify errors | 3
| 10/25 - 11/7 | 5.5 | 4.5 | 1 | 0 - learn to use jest 3 - made required css changes for landing and login pages and created job-listings page of dashboard 5 - reviewed pull requests 7 - Helped teammates with git | 1 |  |  | 2 |  | 0.5 |  | 1 | 1. finished working of job-listings part of the dashboard and finalized landing page 2. created a new branch to push these changes 5. Reviewed PR requests | 1. The team has decided to use keycloaks pages for login signup and forgotpassword | 1. plan is to remove the design for everypage except landing | 1 - finish dashboard | 2
| 11/8-11/15 | 7.5 | 6.5 | 1 | 0 - learn to write unit tests 3 - worked on writing tests 5 - reviewed pull requests 7 - Helped teammates with git | 2 |  |  | 2 |  | 0.5 |  | 2 | 1. started wrote tests | - | -
| 11/16-11/23 | 5.5 | 4.5 | 1 | 0 - learn to write unit tests 3 - finished writing unit tests 5 - reviewed pull requests 7 - Helped teammates with git | 1 |  |  | 2 |  | 0.5 |  | 1 | 1. finished writing tests and setup ci/cd pipeline | - | -
| 11/24-1130 | 4.5 | 3.5 | 1 | 3 - setup ci/cd 5 - reviewed pull requests 7 - Helped teammates with git |  |  |  | 2 |  | 0.5 |  | 1 | 1. updated ci/cd pipeline | - | -
| 12/1-12/8 | 4 | 3 | 1 | 3 - Wrote more tests for more coverage 7 - Helped teammates with git, prepared documents |  |  |  | 1 |  |  |  | 2 | 1. wrote more tests for coverage and prepared documents | - | -

## Amruth Reddy
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 4 | 3 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - Disucced in team meeting about the idea, execution 6 - set up git 7 - research similar products, prepare presentation | 0.5 | 0.5 |  |  |  | 1 | 1 |  | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | Encountered a hashing problem | Resolved it by adjusting configuration settings. | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/15-09/21 | 6.5 | 4.5 | 2 | 0 - Continue learning Git and Django, especially focusing on version control and branching. 1 - Refine high-level requirements based on team discussions and finalize the project's direction. 5 - Collaborate in team meetings to discuss UI design, MVP features, security considerations, and assign backend/frontend tasks. 6 - Assist with setting up GitHub protocol, commit guidelines, and ensure all systems are configured correctly. 7 - Explore tech stack (Fastify, Prisma, Redis) and review similar tools to understand potential implementation strategies. | 0.5 | 0.5 |  |  |  | 2 | 1 | 0.5 | 0 - Learning Git and Django: Practiced Git branching, completed advanced Django tutorials. 1 - Requirement Analysis: Contributed to project direction and app focus. 5 - Team Collaboration: Participated in meeting, documented minutes, finalized MVP. 6 - Git Setup: Established GitHub protocol, debugged setup, configured tools. 7 - Tech Stack Research: Researched Fastify, Prisma, Redis, shared insights. | - | - |  | 4
2 | 09/22-09/28 | 4 | 3 | 1 | 0 - Learning Git and Django: Integrate Django with APIs, enhance Git collaboration. 1 - Requirement Analysis: Validate and refine MVP requirements. 5 - Team Collaboration: Review implementation, adjust plans. 7 - Tech Stack Implementation: Implement CRUD with Fastify, Prisma, and test with Redis. | 0.5 | 1 |  |  |  | 1 |  | 0.5 | 1- Write 1 sections of SPPP: Drafted and reviewed a key section of the SPPP 5- Participate in Iteration 0 presentation: Actively participated in the presentation, contributed to discussing the UI design, tech stack, and MVP features. | - | - | 0 - Learning Git and Django: Continue improving Django skills with a focus on forms and advanced Git commands. 1 - Requirement Analysis: Refine the project’s requirements and finalize MVP feature details. 5 - Team Collaboration: Prepare for the next meeting by reviewing progress and addressing any blockers. 6 - Git Setup: Ensure all team members are following Git commit protocols and resolve any Git-related issues. 7 - Tech Stack Implementation: Start building backend routes with Fastify, integrate Prisma, and test Redis caching functionality. | 5
4 | 09/28-10/2 | 6 | 4 | 2 | 0 - Learning Figma and React: Explore Figma's design capabilities and React fundamentals to support front-end development. 1 - Requirement Analysis: Review and refine UI/UX requirements for the MVP based on team feedback. 5 - Team Collaboration: Participate in design discussions, finalize components in Figma, and adjust implementation plans with the team. 7 - Tech Stack Implementation: Contribute to the initial setup of React components and integrate with the existing design framework in Figma. | 1 | 1 |  |  |  | 1 |  | 1 | Contributed to the initial setup of React components and integrated Figma designs into the project. Participated in requirement analysis to refine the UI/UX for the MVP. Supported team discussions and helped adjust the implementation plan based on Figma's design framework. | - |  | Continue refining UI/UX design elements in Figma. Deepen knowledge of React and implement additional front-end components. Collaborate with the team to finalize MVP requirements and start planning for integration with the back-end. | 5
5 | 10/3-10/09 | 6 | 4 | 2 | 0 - Learning React and Figma: Deepen understanding of React component structure and enhance design skills in Figma. 1 - Requirement Analysis: Collaborate with the team to refine the front-end and back-end integration requirements. 5 - Team Collaboration: Lead the creation of the project presentation and coordinate with team members to ensure all deliverables are on track. 7 - Tech Stack Implementation: Implement additional React components and begin integrating designs from Figma into the React codebase. | 1 | 1 |  |  |  | 1 |  | 1 | Led the creation of the project presentation for the upcoming review. Integrated new React components with designs from Figma, enhancing the front-end interface. Worked on refining and validating the integration of the front-end with the back-end components. | - | - | Finalize integration of front-end designs with React components. Begin working on connecting front-end components to APIs. Collaborate with the team to improve the overall user flow in the application. | 5
6 | 10/10-10/17 | 5 | 5 | 0 | 0 - Learning React: Continue learning advanced React techniques and best practices for UI development. 1 - Requirement Analysis: Review the project’s risk management plan and ensure all requirements are properly aligned with team objectives. 5 - Team Collaboration: Participate in team meetings to discuss progress, provide updates on UI design, and adjust timelines where necessary. 7 - Tech Stack Implementation: Finalize React components, refine the integration of Figma designs, and handle risk management documentation. | 1 | 1 |  |  |  | 1 |  | 2 | Finalized the React components and ensured proper integration with Figma designs. Took ownership of risk management documentation, identifying potential risks and mitigation strategies. Participated actively in team meetings and helped adjust timelines for upcoming tasks. | - | - | Focus on further optimizing React components and improving design integration. Work on handling edge cases in UI and ensuring consistency across the platform. Assist the team in preparing for the upcoming sprint, contributing to planning discussions. | 6
7 | 10/18 - 10/25 | 6 | 3 | 3 | 0 - Focused on understanding analysis requirements and tools, reviewing tutorials and documentation. 5 - Attended team meetings, discussed analysis needs with team members. | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | Focused on learning tasks for analysis section | Limited understanding of analysis requirements and tools; need mentorship | Engage in learning resources and connect with team members for guidance | Continue learning analytics concepts and tools needed for the analysis section, start initial implementation | 6
8 | 10/25 - 11/7 | 6 | 3 | 3 | 0 - Continued learning with more in-depth exploration of analysis methods and tools. 5 - Participated in discussions for integration and analysis planning with the team. | 2 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | Progressed in learning analytics requirements | Need more familiarity with analysis tools and approaches | Continue engaging with resources and peer guidance | Apply initial concepts learned to set up the foundation for analysis tasks | 7
9 | 11/8-11/15 | 7.5 | 6.5 | 1 | 0 - Learn to write unit tests 3 - Wrote tests 5 - Reviewed pull requests 7 - Helped teammates with Git | 1 |  |  | 3 |  | 2 |  | 1 | 1. Started writing tests 2. Enhanced role-based routing for security features | Focused on testing approaches | Continue exploring testing best practices. | 1. Complete unit tests 2. Improve routing logic for better security. | 6
10 | 11/16-11/23 | 5.5 | 4.5 | 1 | 0 - Continued learning unit tests 3 - Finished writing tests 5 - Reviewed pull requests 6 - Researched security enhancements | 1 |  |  | 3 |  | 0.5 | 1 |  | 1. Finalized tests 2. Strengthened application security | No major issues encountered | Monitor security updates. | 1. Work on enhancing tests 2. Expand security measures. | 5
11 | 11/24-1130 | 4.5 | 3.5 | 1 | 3 - Implemented deletion features 5 - Reviewed pull requests 7 - Supported teammates with Git |  |  |  | 2 |  | 1 |  | 1 | 1. Integrated "delete" functionality for all entities | Minor Git conflicts resolved | Improved Git coordination. | 1. Continue testing features 2. Work on frontend security patches. | 4
12 | 12/1-12/8 | 4 | 3 | 1 | 3 - Expanded test coverage 5 - Documented testing process and role-based routing 7 - Supported teammates with Git |  |  |  | 3 |  | 0.5 |  | 0.5 | 1. Expanded test coverage 2. Delivered documentation on implemented features | Documentation pending | Prepare detailed documentation. | 1. Complete documentation 2. Collaborate on final presentation. | 5

## Shubh Gupta
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 5 | 3 | 2 | 0 - Researched about testing methods and automation. 1 - Explored Prettier and Eslint 6 - Setup git and updated a file | 1 |  | 1 |  |  |  | 1 |  | Discussed testing methods and ways to automate it in the application. Explored Prettier and ESlint for the same. Setup Git, Cloned the team repo on local machine and updated the Team.md file. | - | - | 0 - Research about different types of testing methods and deffects and ways to handle them. 1 - Ways to automate testing 4 - Finalizing testing metrics | 5
2 | 09/15-09/21 | 5 | 4 | 1 | 0 - Research about different types of testing methods and deffects and ways to handle them. 1 - Ways to automate testing 4 - Finalized testing metrics | 2 | 2 | [6 empty] | Learnt about Unit testing, Integration tesing and react specific tesing. Finalized Prettier and Eslint for automating code formatting. Finalised the testing metrics for the project going forward and the code review process before pushing anything to the main branch. | - | - | 6 - With Tushar and Faizan's help, setup the development environment including Docker, Redis, Postgres, Postman, Prisma, etc. 3 - Configured project-level Prettier and Eslint for monorepo and added precommit git hook for formatting | 5
3 | 09/22-09/28 | 8 | 6 | 2 | 6 - With Tushar and Faizan's help, setup the development environment including Docker, Redis, Postgres, Postman, Prisma, etc. 3 - Configured project-level Prettier and Eslint for monorepo and added precommit git hook for formatting |  |  |  | 4 |  |  | 2 |  | Setup the development enviroment including react, docker, and postman. Finalized Prettier and eslint for automated code formatting including plugins for node recommended formatting, react recommended formatting and typescript recommended formatting |  |  | start coding for the design components. | 5
4 | 09/28-10/2 | 7 | 5 | 2 | 2 - Split design elements with Hemant and started creating them. 7 - worked on the UML diagrams for the application. |  |  | 2 |  |  |  |  | 3 | Split the design components of the web application and started working on them individually based on the figma designs |  |  | make tests for elements and pages | 3
5 | 10/3-10/09 | 6 | 4 | 2 | 4 - Created Tests for pages along with Jaindra |  |  |  |  | 4 |  |  |  | Created the tests for all the pages using jest. |  |  | create the resume analysis feature using langchain | 4
6 | 10/10-10/17 | 3 | 3 | 0 | 3 - Created Payment Page UI (branch = payment-page) 6 - Configured Tailwind |  |  |  | 3 |  |  |  |  | Created Payment Page in React with Tailwind CSS for rapid and dynamic styling | -Had difficulties configuring tailwind -Ran into errors pushing it to git | All issues resolved | 0 - Learning about test implementation | 5
7 | 10/18 - 10/25 | 1.5 | 1.5 | 0 | 0 - Learnt about implementing different kinds of tests. | 1.5 | [7 empty] | Learnt abount implementing unit tests and implementation tests in the application. |  |  | 3 - Create the Shortlists page for the Dashboard | 7
8 | 10/25 - 11/7 | 7 | 6 | 1 | 3 - Created the Recruiter Shorlists Page (branch = shortlists) 4 - Created Test Case for Recruiter Shortlist page. |  |  |  | 4 | 2 |  |  |  | Created the Recruiter Side Shortlist page with React with Material UI. This will be used by Recruiters to select the job application and move them to a shortlist table. Also Created it's test case using Jest. | - | - | UI Updates | 7
9 | 11/8-11/15 | 3 | 2 | 1 | 3 - UI update, Job Listing page |  |  |  | 2 |  |  |  |  | Updated UI, changed the design of the Job Listing Page where the job used to be visible in cards format and this was changed to be a stack of job. |  |  | Implement user group based routing
10 | 11/16-11/23 | 5.5 | 4.5 | 1 | 3 - Implemented user group based routing, 4 - Manually Tested Group Based Routing |  |  |  | 4 | 0.5 |  |  |  | The initial design showed all the pages to both the user(applicant) and the recruiter, I changed this to be user group based. | Keycloak key errors | Issue resolved, it was a local enivronment setup issue | Implementing Deletion and Updation
11 | 11/24-1130 | 4.5 | 3.5 | 1 | 3 - Implemented Deletion in all entities in the application. |  |  |  | 2 | 1.5 |  |  |  | Implemented "delete" feature for deleting things like resumes, job descriptions, etc | Backend Integration Issues | Issues resolved, entities get deleted from the dataabase as well | Implement Updation and features like create JD and edit profile
12 | 12/1-12/8 | 8 | 7 | 1 | 3 - Implemented Updation in all entities in the application. 3 - Added "Add Job Description" feature. 3 - Added Apply feature in the application side. |  |  |  | 6 | 1 |  |  |  | Designed and Added features to update Profile information, added a "add job description" button and form in the Job Listings page, Added an "Apply" feature in the applicant side where users can apply to a job using any of the uploaded resumes.

## Hemant Krishnakumar
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/8-09/14 | 6 | 4 | 2 | 0 - learn git and figma, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | 1 |  |  |  | 0.5 | 1 | 0.5 | Learnt and set up git, defined high level requirements, made a draft plan and did basic research on the project | - | - | 0 - learn react 1 - continue to define requirements 3 - implement a designs on Figma | 5
2 | 09/15-09/21 | 7.5 | 5.5 | 2 | 0 - learn react 3 - implement designs for figma 5 - send reminders to the team and provided support 6 - setup full stack and env | 1 |  |  | 3 |  | 0.5 | 1 |  | Completed initial designs, environment setup, and team coordination | Difficulty in setting up the full stack | Resolved with team and additional support | 0 - learn react 1 - continue to define requirements 3 - continue Figma design 6 - finish setting up env | 5
3 | 09/22-09/28 | 8.5 | 6.5 | 2 | 0 - learn react 3 - implement designs for figma 5 - send reminders to the team and provided support 6 - setup full stack and env 7 - prepare documents | 1 |  |  | 3 |  | 0.5 | 0.5 | 1.5 | Implemented React components, completed Figma designs partially, continued full stack environment setup, and prepared documentation | Encountered difficulties with integrating frontend designs with backend setup | In progress, working with team members to resolve integration challenges and refine setup | 1 - plan sprints 3 - finish figma disgn for MVP 3 - start creating react component codes | 5
4 | 09/28-10/2 | 8.5 | 6.5 | 2 | 0 - learn react 3 - implement designs for figma 5 - send reminders to the team and provided support, reviewed PRs 6 - setup full stack and env | 1 |  |  | 3 |  | 1 | 1 | 0.5 | Learnt and set up react, altered figma front end designs and setup the full stack environment | - | - | 0 - learn react 3 - implement designs for figma 5 - send reminders to the team and provided support 6 - setup full stack and env | 5
5 | 10/3-10/09 | 8 | 6 | 2 | 0 - learn react 3 - implement designs for figma 5 - send reminders to the team and provided support, reviewd PRs 6 - setup full stack and env | 1 |  |  | 3 |  | 1 | 1 |  | Learnt and set up react router, altered figma front end designs and setup the full stack environment | Difficulty in setting up the react router error free | Researched and deebugged errors | 0 - learn react 5 - send reminders to the team and provided support 6 - setup full stack and env 7 - prepare documents | 5
6 | 10/10-10/17 | 4.5 | 4.5 | 0 | 0 - learn react 5 - send reminders to the team and provided supportm reviewd PRs 6 - setup full stack and env 7 - prepare documents | 1 |  |  |  |  | 1 | 0.5 | 2 | Learnt and set up react and created 4 pages, setup the full stack environment, and prepared documentation | - | - | 0 - learn typescript 5 - send reminders to the team and provided support 7 - prepare documents | 5
7 | 10/18-10/25 | 8.5 | 8.5 | 0 | 0 - learn typescript 3 - implemeted react for 2 pages 5 - send reminders to the team and provided supportm reviewd PRs 6 - setup full stack and env 7 - prepare documents | 1 |  |  | 4 |  | 1 | 0.5 | 2 | Learnt TypeScript and implemented React for two pages, set up the full stack environment, prepared documentation, and provided support by sending reminders and reviewing PRs. | Difficultly in seeing the outputs due to env errors | Researched and deebugged errors | 0 - learn typescript 3 - implemented typescript for 1 major page 5 - send reminders to the team and provided supportm reviewd PRs 6 - setup full stack and env 7 - prepare documents | 7
8 | 10/25-11/7 | 8.5 | 7.5 | 1 | 0 - learn typescript 3 - implemented typescript for 1 major page 5 - send reminders to the team and provided supportm reviewd PRs 6 - setup full stack and env 7 - prepare documents | 1 |  |  | 3 |  | 1 | 0.5 | 2 | Learnt TypeScript, implemented it for one major page, set up the full stack environment, prepared documentation, and provided support by sending reminders and reviewing PRs. | - | - | 0 - learn typescript 3 - implemented typescript for 1 major page 5 - send reminders to the team and provided supportm reviewd PRs 6 - setup full stack and env 7 - prepare documents | 7
9 | 11/8-11/15 | 7.5 | 6.5 | 1 | 0 - learn to write unit tests 3 - worked on writing tests 5 - reviewed pull requests 7 - Helped teammates with git | 2 |  |  | 2 |  | 0.5 |  | 2 | Learned how to write unit tests, worked on writing tests, reviewed pull requests, and helped teammates with Git. | - | - | 0 - learn to write unit tests 3 - worked on writing tests 5 - reviewed pull requests 7 - Helped teammates with git | 7
10 | 11/16-11/23 | 5.5 | 4.5 | 1 | 0 - learn to write unit tests 3 - finished writing unit tests 5 - reviewed pull requests 7 - Helped teammates with git | 1 |  |  | 2 |  | 0.5 |  | 1 | Learned to write unit tests, completed writing them, reviewed pull requests, and supported teammates with Git. | - | - | 0 - learn to write unit tests 3 - finished writing unit tests 5 - reviewed pull requests 7 - Helped teammates with git | 5
11 | 11/24-1130 | 4.5 | 3.5 | 1 | 3 - setup ci/cd 5 - reviewed pull requests 7 - Helped teammates with git |  |  |  | 2 |  | 0.5 |  | 1 | Set up CI/CD, reviewed pull requests, and helped teammates with Git. | - | - | 3 - setup CI/CD 5 - reviewed pull requests 7 - Helped teammates with git | 5
12 | 12/1-12/8 | 4 | 3 | 1 | 3 - Wrote more tests for more coverage 7 - Helped teammates with git, prepared documents |  |  |  | 1 |  |  |  | 2 | Worked on writing additional tests for better coverage, helped teammates with Git, and prepared documentation. | - | - | 3 - Wrote more tests for more coverage 7 - Helped teammates with git, prepared documents
-